## minutes
| session | issue_id | item_description | responsible_party | start_date | due_date | project_id | stakeholders_mentioned
0 | 1 | 1 | Both sides agreed that the Thai PM's visit to China in December 2014 catalyzed the NongKhai-NakornRatchasima-KaengKhoi-MapTaPhut and KaengKhoi-BKK. | both |  |  |  | 5
1 | 1 | 1 | The railway project shall be partitioned into four routes: (1) BKK-KaengKhoi, (2) KaengKhoi-MapTaPhut, (3) KaengKhoi-NakornRatchasima, (4) NakornRatchasima-NongKhai | both | 2015-01-21
2 | 1 | 2 | China agreed to provide experts from the China Railway Group to support with the feasibility study | cn | 2015-01-21 |  |  | 105
3 | 1 | 2 | The feasibility study for the first two routes should be completed by Sep 2015, then the resulting study should be endorsed by both sides by the end of 2015. | both | 2015-01-21 | 2015-09-30 | 1,3
4 | 1 | 2 | The feasibility study for the third and fourth routes should be completed by 2016 | both | 2015-01-21 | 2016-12-31 | 1,2
5 | 1 | 3 | Both sides will discuss how to cooperate on the project and the framework for project funding | both | 2015-01-21
6 | 1 | 3 | Both sides will designate a financial institution from their side to negotiate on financial matters after the feasibility study has been completed | both
7 | 1 | 4 | Thailand will be responsible for the land expropriation | th | 2015-01-21
8 | 2 | 2 | China will send experts to help with conducting feasibility study. This will include surveying and engineering design. Thailand will provide the necessary information. | cn | 2015-02-11 | 2015-02-28
9 | 2 | 1 | Thailand will be responsible for the environmental impact assessment (EIA) | th | 2015-02-11
10 | 2 | 1 | Planned the feasibility study for the first two routes | both | 2015-01-21 | 2015-09-30 | 1,3
11 | 2 | 1 | Planned the study for the third route and the fourth routes | both | 2015-01-21 | 2016-12-31 | 1,2
12 | 2 | 1 | China Raiway Corporation will set-up a consortium to conduct business related to construction, equipment, materials, and control system | cn | 2015-01-21 |  |  | 101
13 | 2 | 1 | Third Railway Survey and Design Institute Group Corporation (TSDI) will be responsible for the engineering design | cn | 2015-01-21 |  |  | 102
14 | 2 | 1 | China Railway Construction Corporation (CRCC) and China Railway Engineering Corportation (CREC) will be responsible for the construction works | cn |  |  |  | 103,104
15 | 2 | 1 | China Railway Group Limited will be responsible for the manufacturing of the train components and equipment | cn |  |  |  | 105
16 | 2 | 1 | China Railway Highspeed (CRH) will be responsible for the signal and control systems | cn |  |  |  | 106
17 | 2 | 1 | China proposed two forms of cooperation: (1) engineering, procurement, construction contract (EPC) and (2) Public-Private Partnership (PPP) | cn |  | n.a
18 | 2 | 3 | Both sides discussed funding options for Thailand which included domestic funding or getting a favorable loan from China. Soft loans and commercial loans were also discussed. | th
19 | 2 | 3 | Thailand will be responsible for the cost of expropriation | th
20 | 2 | 3 | Thailand will be responsible for the cost of EIA | th
21 | 2 | 3 | The China Export and Import Bank (CEXIM) and the Ministry of Finance (Thailand) will discuss the financial matters and the related conditions | both |  |  |  | 201,25
22 | 2 | 3 | The Thai working group will seek an approval from the Thai government regarding the investment structure and fund sources | th
23 | 2 | 1 | China will be responsible for the following: construction along the mountainous areas, tunnel boring, rail system, signaling system, and control system | cn
24 | 2 | 1 | China will operating the high-speed train system during the first route until Thailand is ready to operate the system | both
25 | 2 | 1 | The feasibility study for the BKK-KaengKhoi route will be completed by August 2015 | both |  | 2015-08-31
26 | 2 | 1 | Agreed on the target date to complete the feasibility study for the BKK-KaengKhoi route and the KaengKhoi-MapTaPhut route | th |  | 2015-07-31
27 | 2 | 1 | Agreed on the start date and end date for the construction for the BKK-KaengKhoi route and the KaengKhoi-MapTaPhut route (the end date is 30 months from October 2015) | th | 2015-10-31 | 2018-04-30
28 | 2 | 1 | Agreed on the target date to complete the feasibility study for the KaengKhoi-NakornRatchasima route and the NakornRatchasima-NongKhai route | th |  | 2015-12-31 | 1,2
29 | 2 | 1 | Agreed on the start date and end date for the construction of the KaengKhoi-NakornRatchasima route and the NakornRatchasima-NongKhai route (the end date is 36 months from January 2016) | th | 2016-01-01 | 2019-01-01 | 1,2
30 | 2 | 2 | China agreed to provide technology transfer related to railway construction, control system, electrical system, maintenance, and railway operation | cn
31 | 2 | 1 | China agreed to consider Thailand's proposal for China to build a manufacturing plant for parts and set-up a maintenance center in Thailand | cn
32 | 2 | 1 | China agreed to accept Thailand's proposal to develop Thailand into the regional railway hub for ASEAN | cn
33 | 3 | 1 | CRC and CRCC will be responsible constructing the BKK-KaengKhoi route and the KaengKhoi-MapTaPhut route [first route and second route] | cn |  |  | 1,3 | 101,103
34 | 3 | 1 | Agreed on the target date for the survey work [first route and second route] | both |  | 2015-08-31 | 1,3
35 | 3 | 4 | Agreed to have the contract finalized [first route and second route] | both |  | 2015-09-30 | 1,3
36 | 3 | 4 | Agreed to have the Thai cabinet approve the contract by November 2015 [first route] | thai |  | 2015-11-30 | 1 | 36
37 | 3 | 1 | Agreed that the construction of the first route and the second route will take 2.5 years | both |  |  | 1,3
38 | 3 | 1 | Agreed that the commercial date of operation will be in March 2018 [first route and second route] | both |  | 2018-03-30 | 1,3
39 | 3 | 1 | CRC and CRCC will be responsible constructing the KaengKhoi-NakornRatchasima route and the NakornRatchasima-NongKhai route [third route and fourth route] | cn |  |  | 1,2,3 | 101,103
40 | 3 | 1 | Agreed on the target date for the survey work [third route and fourth route] | both |  | 2015-12-31 | 1,2
41 | 3 | 4 | Agreed to have the contract finalized [third route and fourth route] | both |  | 2016-01-28 | 1,2
42 | 3 | 4 | Agreed to have the Thai cabinet approve the contract by February 2016 [third route and fourth route] | thai |  | 2016-02-28 | 1,2 | 36
43 | 3 | 1 | Agreed that the commercial date of operation will be in December 2018 [third route and fourth route] | both |  | 2018-12-31 | 1,2
44 | 3 | 1 | Agreed to have the construction begin in early 2016 (assumed to be first quarter) | both | 2016-03-31 |  | 1,3
45 | 3 | 1 | Agreed that the construction of the third route and fouth route will take 3 years | both |  |  | 1,4
46 | 3 | 1 | Agreed to have Thailand responsible for the civil works | thai
47 | 3 | 1 | Agreed to have China responsible for system work | cn
48 | 3 | 1 | Agreed to have a joint responsibility for the operation and maintenance | both
49 | 3 | 3 | Agreed that the funding sources will include the Thai national budget, domestic loans, and a favorable loan from China. A thorough discussion on funding will commence after the completion of surveying and design works. | thai
50 | 3 | 2 | China will provide technical training for the Thai personnel | cn
51 | 4 | 2 | CRC reported the progress on the feasibility study and provided preliminary information on the speed limit, the location of stations, the potential railway locations, and operation and maintenance planning | cn |  |  |  | 101
52 | 4 | 1 | Thailand presented the progress on drafting the scope of work | th
53 | 4 | 4 | Thailand discussed measures to ease regulatory burden related to importing equipment for sub-soil survey and inspection, and measures to facilitate visa application process for Chinese personnel | th
54 | 4 | 2 | Both sides agreed to set-up a technical training on construction and operation for the BKK-KaengKhoi-NongKhai and the KaengKhoi-MaptaPhut route for 200 management-level officials and 200 technicians. The training will comprise 6 modules on topics such as railway management and maintenance, locomotive procurement and maintenance, communication and signaling systems, vehicle body and power distribution module. | both
55 | 4 | 2 | Thailand proposed the training be commenced as soon as possible as well as the exchange of specialists | th
56 | 4 | 3 | Thailand will consider the the loan offer from The Import and Export Bank of the People's Republic of China (CEXIM) after the feasibility study has been completed | th |  |  |  | 201
57 | 4 | 3 | The CEXIM proposed that the loan terms will based on the weighted cost of capital according to the Thai and the international financial markets, as well as similar projects that CEXIM had given loans to in the past. | cn |  |  |  | 201
58 | 4 | 1 | Both sides agreed that the CRC and the State Railway of Thailand shall work closely together as well as working in parallel in activities such as planning the locations of train and railway locations, the EIA, the feasibility study etc. such that the construction can begin by October 2015 | both | 2015-10-31 |  | 1,3 | 101,13
59 | 5 | 2 | China reported the progress on the feasibility study, the survey and design works, the plan to lay fiber optic cables, the plan for technical trainings | ch
60 | 5 | 2 | Thailand reported the progress of the environmental impact assessment study | th
61 | 5 | 3 | Both sides agreed to set-up a joint-venture to invest in the railway system, the signaling system, and the operation and maintenance service | both
62 | 5 | 3 | China agreed to provide the best loan terms and conditions for Thailand | cn
63 | 5 | 1 | Both sides agreed to expedite the survey and design works and have them completed by July 2015 | both |  | 2015-07-31
64 | 5 | 1 | Both sides agreed to begin construction in October 2015 | both | 2015-10-31
65 | 6 | 2 | Both sides discussed the progress on conducting the feasibility study and the EIA for the BKK-KaengKhoi route and the KaengKhoi-NakornRatchasima routes and agreed that the studies should be completed by August 2015 | th |  | 2015-08-31 | 1
66 | 6 | 1 | Both sides agreed to select the railway and station locations such that the construction can begin in October 2015 | both |  | 2015-10-31
67 | 6 | 1 | Both sides agreed to establish the Operation Control Center (OCC) which will be operational for both the 1.435-m track and the 1-m track | both
68 | 6 | 3 | Both sides agreed to have the State Railway of Thailand (SRT) establish a joint venture with a Chinese railway entity to invest in the railway system, operation and maintenance, and civil work | both |  |  |  | 107
69 | 6 | 3 | The CEXIM will provide details on the loan terms and conditions to Thailand | cn |  |  |  | 201
70 | 6 | 2 | Beijing Jiaotong University will provide short-term training sessions for executive-level officials and future trainers in 2015 | cn |  | 2015-12-31 |  | 202
71 | 6 | 2 | Beijing Jiaotong University will provide medium-term and long-term training sessions in 2016 | cn |  | 2016-12-31 |  | 202
72 | 7 | 1 | Thailand requested China to revise the cost and estimated revenue of the BKK-NakornRatchasima route and re-submit within one month | cn |  | 2015-10-12 | 1
73 | 7 | 2 | China will submit the feasibility studies for the second route and the fourth route within November 2015, which is one month earlier than planned | cn |  | 2015-11-30 | 2,3
74 | 7 | 2 | The State Railway of Thailand will hire an external consultant to review the feasibility studies by China | th |  |  |  | 107
75 | 7 | 1 | The construction date for the BKK-KaengKhoi route [first route] and the KaengKhoi-NakornRatchasima route will have to postpone from October 23, 2015 until the feasibility studies have been finalized. [postponed from 2015-10-23 to the feasibility studies finalized] | both |  |  | 1
76 | 7 | 1 | Both sides agreed that the high-speed railway project shall proceed using EPC contracts | both
77 | 7 | 3 | China confirmed that the loan terms and conditions will be the most favorable compared to other options | cn
78 | 7 | 4 | The Thai Public Debt Management Office (PDMO) will notify China on the process for the Thai government to borrow money from foreign sources | th |  |  |  | 203
79 | 7 | 2 | Thailand sent the first batch of officials to attend a training session in China and will send the second batch to train in October 2015 | cn
80 | 7 | 1 | Both sides agreed to publicize the China-Thailand railway cooperation by facilitating technical workshops and invite the media to attend | both
81 | 8 | 4 | Both sides agreed on the principles underlying the cooperation framework between China and Thailand on railway development and will seek an approval from their respective governments within two weeks | both | 2015-10-28 | 2015-11-15
81 | 8 | 1 | Both sides agreed on the principles underlying the cooperation framework between China and Thailand on railway development and will seek an approval from their respective governments within two weeks
82 | 8 | 1 | Both sides agreed to have the groundbreaking ceremony to mark the construction of the Operation Control Center (OCC) tentatively between December 15-20, 2015 | both | 2015-10-28 | 2015-12-20 |  | 107
83 | 8 | 1 | Both sides agreed to have a promotional event for the public to learn about the project during the OCC groundbreaking ceremony | both | 2015-10-28 | 2015-12-20
84 | 8 | 1 | Both sides agreed to set the tentative start date for the railway construction in Novermber 2016 (after finalizing the decisions on contractor selection, project cost, and financial terms) | both |  | 2016-11-30
85 | 8 | 2 | China agreed to revise the feasibility studies according to comments by Thailand and will re-submit the studies by the agreed due date | cn
86 | 8 | 1 | China will deliver the design works for the [first route] by November 2015 | cn |  | 2015-11-30 | 1
87 | 9 | 1 | Both sides agreed to have the groundbreaking ceremony to mark the construction of the Operation Control Center (OCC) on December 19, 2015 with the cooperation of the Joint Working Group between the State Railway of Thailand and CRC. | both | 2015-10-28 | 2015-12-19 |  | 107,101
88 | 9 | 1 | Both sides agreed to set-up the date for the promotional event during the OCC groundbreaking ceremony on December 16, 2015 | both | 2015-10-28 | 2015-12-16
89 | 9 | 1 | China will send experts to attend the promotional event | both | 2015-10-28 | 2015-12-16
90 | 9 | 2 | OTTPP requested China to revise the feasbility studies and re-submit by February 8, 2016 | cn | 2015-10-28 | 2016-02-08 |  | 204
91 | 9 | 4 | The Minister of Transport (Arkom) and Vice-Chairman, National Development and Reform Commission signed the cooperation framework between China and Thailand on railway development | both |  |  |  | 8,7
92 | 10 | 3 | Thailand will be the sole investor in the BKK-NakornRatchasima route | th | 2016-03-23 |  | 1
93 | 10 | 1 | Thailand requested China to revise down the project costs and shorten the project timeline | cn
94 | 10 | 1 | China agreed to revise the project costs and the timeline, then resubmit the proposal within one week | cn |  | 2016-05-19
95 | 10 | 3 | Thailand will be the sole project financier according to what was discussed between the leaders of the two countries (does not mention who the leaders were) | th
96 | 10 | 4 | Both sides agreed to breakdown the EPC contracts into a civil work contract (EPC-1) and a railway and high-speed train contract (EPC-2) | both
97 | 10 | 1 | Thailand will be responsible for the civil work contract (EPC-1) by hiring domestic contractors | th
98 | 10 | 1 | China, with an approval from Thailand, will select a chinese SOE to accept the EPC-2 contract | cn
99 | 10 | 1 | China will also select a chinese SOE to develop the construction drawing for Thailand to select domestic contracts for EPC-1 | cn
100 | 10 | 2 | Both sides agreed to jointly monitor the qualilty of the construction | both
101 | 10 | 2 | Both sides agreed to begin the civil works by September 2016 | both |  | 2016-09-30
102 | 10 | 1 | Thailand will establish a company to be the high-speed train operator | th
103 | 10 | 2 | China will provide technical training to the Thai operator company and support with the operational management of the rail system | cn
104 | 10 | 3 | Thailand will take loans from China to procure the high-speed rail system | th
105 | 10 | 3 | China agreed to provide a favorable loan term | cn
106 | 11 | 1 | The BKK-Ratchasima is designated as the first route and is to begin in September 2016.Both sides agreed to break down the construction into minor routes. | both |  |  | 1
107 | 11 | 3 | Both sides agreed on the estimated project cost as jointly proposed by the SRT and the CRIC | both |  |  | 1 | 107,108
108 | 11 | 1 | Thailand will negotiate with China on the second EPC contract and reach an agreement before the next meeting | both |  | 2016-07-31 | 1
109 | 11 | 3 | Thailand asserted that the loan currency provided by the CEXIM must be in accordance with the second EPC contract | th |  |  | 1 | 201
110 | 11 | 3 | Both sides agreed on the preliminary loan terms: currency will be RMB and the interest rate shall be cheaper than the market could offer | both |  |  | 1
111 | 11 | 3 | CEXIM will submit a loan proposal for discussion during the next meeting. The proposal will be based on both RMB and USD. | cn |  | 2016-07-31 | 1 | 201
112 | 11 | 3 | Thailand requested China to support with the costs associated with the feasbility studies | th |  |  | 1
113 | 12 | 3 | Both sides agreed on the estimated cost for the BKK-NakornRatchasima route | both |  |  | 1
114 | 12 | 3 | Both sides disagreed on the costs associated with the conducting the feasibility studies and costs associated with the technical trainings | both |  |  | 1
115 | 12 | 4 | Both sides agreed to closely monitor the progress on drafting the second EPC contract as some issues remained to be resolved | both
116 | 12 | 2 | China will begin the engineering design work after relevant contracts have been signed or receiving a letter of approval from the State Railway of Thailand | cn |  |  | 107
117 | 12 | 2 | China presented the technical studies as the basis for engineering design works | cn
118 | 12 | 2 | Thailand will provide feedbacks on the technical studies by August 15, 2016 | th |  | 2016-08-16
119 | 12 | 1 | Both sides agreed to adhere to the project timeline and to sign the MOU during the next meeting | both |  | 2016-09-30
120 | 12 | 3 | China submitted the loan proposal with terms and conditions based on the RMB currency and the revised contract draft | cn
121 | 12 | 3 | Thailand requested an additional loan proposal which would be based on the USD currency | th
122 | 13 | 4 | Both sides signed the cooperation framework on railway development which will replace the previous document signed on December 3, 2015 | both
123 | 13 | 3 | Both sides agreed on the estimated project cost and will continue to negotiate on the costs associated with conducting the feasibility studies and technical trainings | both
124 | 13 | 2 | China submitted technical training manuals on the railway construction and operation | cn
125 | 13 | 1 | Thailand reiterated its intention to expedite the internal processes such that the project shall be completed on time | th
126 | 13 | 4 | Both sides agreed to apportion the second EPC contract into smaller contracts | both
127 | 13 | 4 | The National Development and Reform Commission will issue a power of attorney to the Chinese state enterprises that will become contract partners with Thailand | cn |  |  |  | 205
128 | 13 | 2 | Thailand will submit preliminary feedbacks on the technical report [first route and third route], which was provided by China, as soon as possible | th |  |  | 1
129 | 13 | 3 | The working group on technical analysis will review the difference in costs between two design options | both
130 | 13 | 3 | Both sides will discuss the loan terms and conditions in detail after the Thai cabinet has approved the project | both |  |  |  | 36
131 | 14 | 4 | Thailand submitted feedbacks on apportioning the second EPC contract (EPC-2) into three sub-contracts: (1) Engineering design (2) Engineering Consulting and (3) Procurement of signalling, maintenance, and training. Both sides should be able to reach an agreement by October 2016 | th
132 | 14 | 2 | China will revise the technical specifications from Chinese standards to the international standards. This would help with comparing the technical specifications to the Thai standards | cn
133 | 14 | 1 | China will include additional information on the design of civil works so the construction cost could be estimated. The goal is to submit the tender document by November 2016 | cn | 2016-11-30
134 | 14 | 1 | Both sides agreed to extend the target costruction of the first route by December 2016, as discussed between the Prime Minster of Thailand and President Xi | both |  | 2016-12-31 | 1 | 5,30
135 | 15 | 2 | Both sides discussed the engineering works for the BKK-NakornRatchasima route. Some issues still remain to be concluded | both | 2016-10-26 | 2016-11-30 | 1
136 | 15 | 1 | China proposed that design works such as connecting the utility, and connecting the road be separated from the scope of work within the contract and outsource these tasks to third parties | cn |  |  | 1
137 | 15 | 2 | China will revise the engineering documents according to the comments received from Thailand | cn |  |  | 1
138 | 15 | 3 | China had submitted a loan proposal based on both USD and RMB currencies to Thailand | cn |  |  | 1
139 | 16 | 2 | China submitted the details on the construction work for the first segment of the BKK-NakornRatchasima route | cn |  |  | 1
140 | 16 | 2 | Thailand had reviewed 90% of the details on the construction work of the first segment of the BKK-NakornRachasima route | th |  |  | 1
141 | 16 | 2 | China is drafting the details on the construction work for the second segment of the BKK-NakornRatchasima route | cn |  |  | 1
142 | 16 | 2 | China will draft the details on the construction work for the third segment and fourth segment of the BKK-NakornRatchasima route after the contract has been signed | cn |  |  | 1
143 | 16 | 2 | China will draft the details on the construction work for the third segment and fourth segment of the BKK-NakornRatchasima route after the design contract has been signed | cn |  |  | 1
144 | 16 | 1 | Both sides will sign a memorandum of cooperation (MOC) for the BKK-NongKhai on January 9, 2017. The Deputy Prime Minister will be attending in China | th |  |  | 2 | 34
145 | 16 | 1 | The memoradum of cooperation (MOC) will address the issue of connecting the BKK-NongKhai to Laos | th |  |  | 4 | 34
146 | 16 | 3 | Thailand reiterated that the loan terms and conditions have to be most favorable | th
147 | 16 | 2 | The project implementation plan for the BKK-NakornRatchasima route is under review by the NESDC | th |  |  | 1 | 24
148 | 16 | 2 | The EIA for the BKK-NakornRatchasima route is under going review by the Ministry of Environment (Thailand) | th |  |  | 1 | 212
149 | 17 | 4 | Both sides agreed on the details within the Contract 2.1 except on financial terms | both |  |  | 1
150 | 17 | 4 | Both sides agreed to discuss the details for the Contract 2.2 and to conclude by May 2017 | both |  | 2017-05-31 | 1
151 | 17 | 1 | Both sides agreed on the principles regarding the procurement of construction materials for the first route of the project | both |  |  | 1
152 | 17 | 1 | Thailand pushed for 11 out of 12 materials to be procured domestically | th
153 | 17 | 2 | China will provide the technical details on rebar (steel) which is a material that cannot be procured domestically | cn
154 | 17 | 2 | China will support Thailand with communicating the technical specifications to steel manufacturers in Thailand | cn
155 | 17 | 2 | Thailand will comment on the technical specifications related to the civil work for the first construction route by April 13, 2017 | th |  | 2017-04-13 | 1
156 | 17 | 2 | China will respond to the Thai comments on the technical specifications and reply back within 2017-04-20 | cn |  | 2017-04-20 | 1
157 | 17 | 4 | Both sides agreed to negotiate on the details of Contract 2.3 | both
158 | 17 | 1 | Both sides agreed to try their best to begin construction by July 2017 | both
159 | 18 | 4 | China submitted the technical and pricing proposals for Contract 2.2 | cn |  |  | 1
160 | 18 | 4 | Thailand requested China to revise the costs of specialists for Contract 2.1 in terms of compensation, man hours, and other costs | cn |  |  | 1
161 | 18 | 4 | Thailand acknowledged the specifications and responsibilities of core personnel under Contract 2.1 and Contract 2.2 | th |  |  | 1
162 | 18 | 4 | Both sides discussed the legal aspects of Chinese engineers and architects operating in Thailand. (Licenses are required for engineers and architects in Thailand and Chinese personnel might not have the licenses.) | both
163 | 18 | 4 | Both sides agreed to have legal specialists study the legal aspects of Chinese engineers and architects operating in Thailand under the railway project | both
164 | 18 | 1 | China notified that TSDI has changed its name to CRDC | cn |  |  |  | 102
165 | 18 | 2 | China provided the technical details on rebar (steel), which is a material that cannot be procured domestically | cn
166 | 18 | 2 | Both sides agreed that the technical working group will review the technical details on the rebar (steel) | both
167 | 18 | 1 | Both sides acknowledged that the railway tract under this project cannot be used for connecting Bangsue-Donmuang route | both
168 | 18 | 1 | Thailand confirmed that the Thai Cabinet will approve the necessary documents such as the EIA so the project can begin construction on time | th |  |  |  | 36
169 | 19 | 4 | Both sides agreed on the costs associated with wages within the Contract 2.1 and will seek internal approval for the contract to be signed | both |  |  | 1
170 | 19 | 4 | Both sides agreed to have the Contract 2.1 signed by August 2017 | both |  | 2017-08-31 | 1
171 | 19 | 4 | Both sides agreed to have the Contract 2.2 signed by September 2017 | both |  | 2017-09-31 | 1
172 | 19 | 4 | Both sides agreed to have the Contract 2.3 signed by September 2017 | both |  | 2017-09-31 | 1
173 | 19 | 2 | Both sides agreed on the plan to develop the design works for construction, train systen, etc. | both
174 | 19 | 2 | Both sides agreed on the plan to test the technical systems | both
175 | 19 | 2 | Both sides agreed on the plan to set-up technical training sessions | both
176 | 19 | 4 | China had discussed with the Thailand Council of Engineers and the Thailand Architect Council on training Chinese engineers and architects on the relevant Thai regulations | cn |  |  |  | 207,208
177 | 19 | 4 | Both sides agreed to train and certify Chinese engineers and architects by August 2017 | both |  | 2017-08-31
178 | 19 | 1 | Both sides agreed to foster close cooperation between the Thai engineers/architect councils and the Chinese counterparts(which?) | both |  |  |  | 207,208
179 | 19 | 4 | Both sides agreed to negotiate Contract 2.3 based on the feasibility study provided by China | both |  |  | 1
180 | 19 | 4 | Thailand proposed details within Contract 2.3 related to the estimated project cost, scope of work, maintenance, technology transfer, etc. | th |  |  | 1
181 | 19 | 4 | Both sides agreed to finalize the details of Contract 2.3 by the next meeting | both |  | 2017-08-31 | 1
182 | 19 | 2 | China reiterated its intention to conduct knowledge and technology transfer within bounds described by the rules and regulations of the two countries | cn
183 | 19 | 2 | Both sides agreed to the revised technical specifications for the rebar (steel) material (carbon content, welding capability). This had allowed for domestic sourcing. | both
184 | 19 | 1 | Both sides agreed to plan the BKK-NongKhai high-speed railway project as soon as possible | both |  |  | 2
185 | 20 | 4 | Both sides agreed on the details related to survey, engineering, and civil works within the Contract 2 | both |  |  | 1
186 | 20 | 4 | Both sides agreed to have the Contract 2.1 signed by August 2017 | both |  | 2017-08-31 | 1
187 | 20 | 4 | Both sides agreed to have the Contract 2.2 signed by September 2017 such that the 3.5-km first stage can begin construction by October 2017 | both |  | 2017-09-30 | 1
188 | 20 | 4 | Both sides reached a consensus on the costs associated with the Contract 2.2 | both |  |  | 1
189 | 20 | 4 | Both sides agreed to expedite the negotiation on the terms of reference (TOR) and other details related to the Contract 2.3 (rail work, electrical and mechanical system, train procurement, trainings) and to reach a conclusion by September 2017 | both |  | 2017-09-30 | 1
190 | 20 | 3 | Both sides will implement the project within the estimated project cost of 179,312 million baht | both
191 | 20 | 4 | Both sides agreed on the plan to train and certify chinese engineers and architects. China will finance the training workshops. | both | 2017-09-01 | 2017-11-30
192 | 20 | 2 | Both sides will provide the four training workshops in Tianjin for chinese engineers between September-November 2017 | cn | 2017-09-01 | 2017-11-30
193 | 20 | 2 | Both sides will provide the two training workshops in Thailand for chinese engineers between October-November 2017 | cn | 2017-09-01 | 2017-11-30
194 | 20 | 2 | China agreed to provide technical training and advice to Thai personnel on the high-speed railway technology within what is disclosable | cn
195 | 20 | 2 | Thailand requested access information and know-how related to the high-speed train technology | th
196 | 20 | 4 | Both sides agreed to discuss the issue intellectual property in accordance with international standard and commercial practice | both
197 | 20 | 3 | Both sides agreed that the estimated project cost already covers the cost of technology transfer in civil works | both
198 | 20 | 3 | Both sides agreed that the technology transfer costs excluding civil works will be negotiated later. For example, trainings on project management, operation, and maintenance | both
199 | 20 | 1 | Both sides agreed to have the working group reach a conclusion on the railway routing by August 2017 | both |  | 2017-08-31 | 20
200 | 20 | 3 | Both sides will continue to negotiate on the loan terms and conditions and to reach a conclusion by October 2017 (the loan from China) | both |  | 2017-10-31
201 | 21 | 1 | Both sides agreed to work closely so that the first 3.5 km segment of the BKK-NakornRatchasima route can begin construction by November 2017 | both |  |  | 1
202 | 21 | 1 | Both sides agreed to reach a conclusion on the routing that will connect the Bangsue hub, the Donmuang airport, and the Baan Pa-Chi Station by October 8, 2017 | both |  | 2017-10-08 | 1
203 | 21 | 1 | Thailand requested China to design the station buildings in accordance with the local identity, the domestic architectural style, public acceptance, and local regulations | cn
204 | 21 | 1 | Both sides agreed to begin planning the NakornRatchasima-NongKhai route as soon as possible | both |  |  | 2
205 | 21 | 3 | Both sides reviewed the loan proposal by China and will resolve the remaining disagreement | both
206 | 21 | 4 | Thailand will support China with issuing the visa to chinese personnel such that field survey could be completed on time | th
207 | 22 | 1 | Both sides agreed to begin construction of the 3.5-km (KlangDong-PangAsoke) by December 21, 2017 | both |  | 2017-12-21 | 1
208 | 22 | 1 | Both sides agreed to expedite the NakornRatchasima-Nongkhai route | both |  |  | 2
209 | 22 | 1 | Both sides agreed to use trains capable of reaching 250-km/hr for the NakornRatchasima-NongKhai route | both |  |  | 2
210 | 22 | 2 | Thailand emphasized the importance of conducting a feasibility study for the NongKhai-Vientiene route so that useful information can be incorporated into the NakornRatchasima-NongKhai route | th |  |  | 4
211 | 22 | 3 | Thailand reiterated the project should strictly be within the approved budget of 137,413 million baht | th
212 | 22 | 2 | China agreed to provide a training workshop for Thai middle/senior-level specialists | cn
213 | 22 | 2 | Both sides agreed to enhance the capability of the center for manufacturing, testing, and maintenance of train-parts | both
214 | 22 | 2 | China will send specialists to assess the center for manufacturing, testing, and maintenance of train-parts | cn
215 | 22 | 4 | Both sides agreed to apportion the primary contract on civil works into sub-contracts and set the target date to submit the relevant deliverables | both
216 | 22 | 3 | Both sides reviewed the loan proposal throughly which showed great progress | both
217 | 23 | 1 | Both sides agreed that the technical working group shall shorten the negotiation process and foster closer cooperation | both
218 | 23 | 1 | Thailand agreed not to set-up a secondary railway control center for the first BKK-NakornRatchasima route | th |  |  | 1
219 | 23 | 1 | Both sides agreed to increase the number of computer servers for the train control center at the ChiangRakNoi station for the NakornRatchasima-NongKhai route | both |  |  | 2
220 | 23 | 2 | China requested the project to consider an appropriate back-up power system to support the high-speed train operations | th
221 | 23 | 2 | Thailand will discuss with the MEA, PEA, and EGAT on the back-up power system | th |  |  |  | 209,210,211
222 | 23 | 2 | Thailand acknowledged the comments, submitted by China, on the feasibility study for the project's second route (NakornRatchasima-NongKhai) | th |  |  | 2
223 | 23 | 3 | China will estimated the project for the mechanical system and electrical system for the NakornRatchasima-NongKhai route | cn |  |  | 2
224 | 23 | 2 | China is conducting a preliminary feasbility study for the NongKhai-Vientiane route | cn |  |  | 2
225 | 23 | 1 | China requested arranging a three-country platform (Thai-Laos-China) to discuss the technical details and custom clearance for the NongKhai-Vientiane route | cn |  |  | 4
226 | 23 | 2 | China will prepare a technical training session for Thai engineers on the topic of high-speed train. The session could be provided in Thailand | cn
227 | 23 | 1 | Thailand is considering establishing a new agency to supervise the management of high-speed trains | th
228 | 23 | 2 | Thailand requested technical support from China to establish the new agency | th
229 | 23 | 1 | China is willing to support Thailand in developing the railway industry | cn
230 | 24 | 1 | Both sides agreed that connecting the NongKhai-Vientiane route is of essense | both |  |  | 4
231 | 24 | 1 | Both sides agreed in principle regarding the construction of a new bridge located South of the Thaiâ€“Lao Friendship Bridge | both
232 | 24 | 1 | Thailand proposed a checkpoint for custom clearance, immigration, and other functions on both the Thai and Laos borders. | both
233 | 24 | 2 | China agreed to conduct a feasibility study for the NongKhai-Vientiane route | cn |  |  | 4
234 | 24 | 1 | Both sides agreed to begin construction of the NakornRachasima-NongKhai route in 2019 | both |  | 2019-12-31 | 2
235 | 24 | 2 | Both sides discussed the civil works connecting the Donmuang airport and the Bangsue hub | both
236 | 24 | 2 | Thailand proposed six training modules which focused on training the trainers | cn
237 | 24 | 2 | China reiterated that the technical training sessions will be based on actual train operation and conducted in Thailand | cn
238 | 24 | 3 | China will submit the loan proposal by June 30, 2018 | cn |  | 2018-06-30
239 | 24 | 4 | Both sides will expedite the negotiation process for the Contract 2.3 and to reach a conclusion by August 2018 | both |  | 2018-08-31 | 1
240 | 25 | 2 | Both sides agreed not to use crushed stones for track ballast along the Donmuang airport and Bangsue hub | both |  |  | 1,18
241 | 25 | 4 | China will submit additional information on the technical aspect and the bill of quantity of the Contract 2.3 | cn |  |  | 1
242 | 25 | 4 | Both sides agreed that the technical training section of the Contract 2.3 will address four topics: (1) train operation and maintenance (2) Establishing a training center in Thailand (3) Establishing a testing and inspection center and (4) technology transfer | both |  |  | 1
243 | 25 | 2 | Both sides agreed that capacity building at the testing center in Thailand will greatly benefit the project | both
244 | 25 | 2 | Both sides agreed to have experts from China providing advice and training on the topic of parts testing | both
245 | 25 | 4 | China agreed to provide knowhow on regulating and licensing high-speed train | cn
246 | 25 | 3 | Both sides will continue to negotiate on the loan proposal | both
247 | 26 | 1 | Both sides acknowledged that Thailand is issueing a tender for the Sikhio-KutChik segment (11 km) | both |  |  | 1
248 | 26 | 4 | Both sides agreed on the principles of Contract 2.3 and will make every effort to resolve the remaining disagreements such that the contract is signed by January 2019 | both |  | 2019-01-31 | 1
249 | 26 | 3 | Thailand will absorb the additonal costs associated with not using crushed stone for the track ballast | th
250 | 26 | 1 | Both sides acknowledged the construction of the NakornRatchasima-NongKhai route will begin in 2019 | both |  | 2019-01-31 | 2
251 | 26 | 1 | Thailand will take responsible for civil work design | th
252 | 26 | 2 | Both sides will consider the practicability of having Thailand design the mechanical system and electrical system | both
253 | 26 | 1 | Both sides agreed on the necessity of connecting the NongKhai-Vientiane route and will arrange a three country meeting | both |  |  | 4
254 | 26 | 2 | Both sides agreed on the structure and number of employees (900 employees) for the new high-speed train agency in Thailand | both
255 | 26 | 2 | Thailand requested China prepare a high-speed train operating manual and a maintenance manual | cn
256 | 26 | 2 | Both sides agreed to increase the capacity of testing high-speed train components in Thailand | both
257 | 27 | 1 | Both sides acknowledged the Sikhio-KutChik segment is currently waiting for the construction contract to besigned by March 6, 2019 | both | 2019-03-06 |  | 1
258 | 27 | 1 | Both sides acknowledged the construction of KaengKhoi-NakornRatchasima segment (119.4-km) and the Bangsue-KaengKhoi segment (119-km) will be separated into 12 contracts. Four contracts are expected to be signed by June 2019 | both |  | 2019-06-30 | 1
259 | 27 | 1 | Another seven contracts are expected to be signed by July 2019 | both |  | 2019-07-31
260 | 27 | 4 | Both sides agreed on the core components of the Contract 2.3 and will negotiate to resolve the remaining disagreements | both |  |  | 1
261 | 27 | 4 | Both sides agreed to seek internal approval for the Contract 2.3 and will make every effort to get the contract signed during the Second Belt and Road Initative Meeting in China | both |  |  | 1
262 | 27 | 3 | Both sides agreed to cooperate on financial matters as outlined in the loan proposal, submitted on July 30 2018, by the CEXIM | both |  | 2018-07-30 |  | 201
263 | 27 | 3 | Both sides will resolve the remaining disagreements regarding the loan proposal | both
264 | 27 | 2 | Thailand finished reviewing the feasibility study for the NakornRatchasima-NongKhai route | th |  |  | 2
265 | 27 | 1 | Both sides will discuss how to cooperate for the NakornRatchasima-NongKhai route | both |  |  | 2
266 | 27 | 2 | CRIC will hold a seminar on licensing for the high-speed rail operator between March 2-3, 2019 | cn |  | 2019-03-03 |  | 108
267 | 27 | 2 | Thailand will send personnel to join the seminar by CRIC | th |  |  |  | 108
268 | 27 | 2 | Both sides acknowledged the progress on capacity building and technology transfer | both
269 | 27 | 1 | Both sides agreed to source construction materials as described in the Contract 2.3 from the domestic market as much as possible | both

## Sheet1
1 | 1 | The railway project shall be partitioned into four routes: (1) BKK-KaengKhoi, (2) KaengKhoi-MapTaPhut, (3) KaengKhoi-NakornRatchasima, (4) NakornRatchasima-NongKhai
2 | 1 | Thailand will be responsible for the environmental impact assessment (EIA)
2 | 1 | China Railway Group Limited will be responsible for the manufacturing of the train components and equipment
2 | 1 | China agreed to consider Thailand's proposal for China to build a manufacturing plant for parts and set-up a maintenance center in Thailand
8 | 1 | Both sides agreed on the principles underlying the cooperation framework between China and Thailand on railway development and will seek an approval from their respective governments within two weeks
9 | 1 | China will send experts to attend the promotional event
10 | 2 | China will provide technical training to the Thai operator company and support with the operational management of the rail system
12 | 2 | China presented the technical studies as the basis for engineering design works
16 | 2 | China submitted the details on the construction work for the first segment of the BKK-NakornRatchasima route
16 | 2 | Thailand had reviewed 90% of the details on the construction work of the first segment of the BKK-NakornRachasima route
16 | 2 | China is drafting the details on the construction work for the second segment of the BKK-NakornRatchasima route
22 | 2 | Both sides agreed to enhance the capability of the center for manufacturing, testing, and maintenance of train-parts
22 | 2 | China will send specialists to assess the center for manufacturing, testing, and maintenance of train-parts
23 | 2 | Thailand will discuss with the MEA, PEA, and EGAT on the back-up power system
12 | 3 | Both sides agreed on the estimated cost for the BKK-NakornRatchasima route
13 | 3 | Both sides will discuss the loan terms and conditions in detail after the Thai cabinet has approved the project
15 | 3 | China had submitted a loan proposal based on both USD and RMB currencies to Thailand
16 | 3 | Thailand reiterated that the loan terms and conditions have to be most favorable
22 | 3 | Thailand reiterated the project should strictly be within the approved budget of 137,413 million baht
7 | 4 | The Thai Public Debt Management Office (PDMO) will notify China on the process for the Thai government to borrow money from foreign sources
10 | 4 | Both sides agreed to breakdown the EPC contracts into a civil work contract (EPC-1) and a railway and high-speed train contract (EPC-2)
18 | 4 | Thailand requested China to revise the costs of specialists for Contract 2.1 in terms of compensation, man hours, and other costs
19 | 4 | China had discussed with the Thailand Council of Engineers and the Thailand Architect Council on training Chinese engineers and architects on the relevant Thai regulations