## r16
letter_id | item_description | issue_id | stakeholders_mentioned
1601 | mTransport requests the Cabinet to approve the adjustment to the project cost and request an endorsement for Contract 2.3 worth 51 billion baht. | 3
1601 | Continue 1601. Requests an endorsement for Contract 2.3 worth 51 billion baht. The proposal mentioned that NDRC would select qualified state-owned enterprises to enter the contract. The proposal mentioned that NDRC would select qualified state-owned enterprises to enter the contract | 4 | 213,207,216
1601a | This letter is from the Attorney General to mTransport. Contract 2.3 does not specify the exchange rate and the reference date for exchange rate calculation for the contract price. Therefore, the State Railway of Thailand should consider options to manage the forex risk | 2 | 117
1602 | This letter is from the Attorney General to SOC. The Attorney General has already submitted comments to mTransport. Therefore, there is no further comments on Contract 2.3 at this stage | 0
1603 | This letter is from the NESDC to SOC. This proposal increases the risk of project cost over run. Therefore, mTransport and the State Railway of Thailand should expedite the project so it is completed on time and also closely monitor the project | 1 | 117
1603 | Continue 1603. The State Railway of Thailand, the Bank of Thailand, and mFinance should discuss project funding and forex risk management to minimize impact to the approved budget cost | 3 | 117
1603 | Continue 1603. The State Railway of Thailand should closely follow comments by the Attorney General regarding Contract 2.3 | 0 | 117
1603 | Continue 1603. The State Railway of Thailand should be responsible for the HSRP until a new independent organization has been established. | 1 | 117
1603 | Continue 1603. The State Railway of Thailand should strictly follow the rules so the project is transparent and easy to audit | 4 | 117
1603 | Continue 1603. mTransport and the State Railway of Thailand should report back to the Cabinet every three months on the progress | 1 | 117
1604 | This letter is from the Budget Bureau to SOC. mTransport should follow the recommendation made by the Attorney General on the forex risk | 2
1604 | Continue 1604. The State Railway of Thailand has to carry the finance burden of this project until a new independent organization has been set-up | 1 | 117
1604 | Continue 1604. The proposal to adjust the project cost should be approved by the [Thailand-China] Joint Committee first, before proposing to the Cabinet | 3
1605 | This letter is from mEnvironment to SOC. The State Railway of Thailand has not submitted a revised EIA report for the Bangkok - Nakorn Ratchasima route. According to the environmental act, the EIA report must be approved first before Contract 2.3 can be signed | 2 | 117
1606 | This letter is from mFinance to SOC. The contract cost has to include all the taxes | 3
1606 | Continue 1606. The State Railway of Thailand should plan to manage forex risk | 2 | 117
1606 | Continue 1606. mTransport and the State Railway of Thailand should carefully follow the relevant rules and regulations for the benefit of the country when executing this project | 4 | 117
1606 | Continue 1606. The State Railway of Thailand is to incure the financial burden with loans sourced by mFinance until a new independent organization has been established | 3 | 117
1606 | Continue 1606. Before any budget adjustment to Contract 2.3, the Cabinet must grant an endorsement first | 4
1607 | This letter is from mInnovation to SOC. The project should be closely monitored to prevent a cost over run. There should also be a plan inplace to manage forex risk | 2

## r15
letter_id | item_description | issue_id | stakeholders_mentioned
1501 | mTransport requests the Cabinet to approve 797 million baht from the central budget for engineering design (civil works) for the Nakorn Ratchasima - Nong Khai route | 3
1501a | This letter is from Budget Bureau to mTransport. The Prime Minister has endorsed the budget request. Consequently, the State Railway of Thailand should proceed with the disbursement process according to the relevant rules and regulations | 4 | 117
1502 | This letter is from NESDC to SOC. NESDC supports this proposal. The appropriation of annual government expenditure should follow guidelines from the Budget Bureau | 4 | 117
1502 | Continue 1502. The State Railway of Thailand should reschedule the trains and revise the timing of its investments because the State Railway of Thailand is also requesting the Cabinet to approve another railway route (not high-speed) connecting Khon Khen - Nong Khai | 1 | 117
1503 | This letter is from Budget Bureau to SOC. The Budget Bureau supports the proposal. Meanwhile, the State Railway of Thailand should discuss the details with the Budget Bureau regarding budgeting for the next fiscal year | 3 | 117
1503 | Continue 1503. The project cost that is required to commit across fiscal years is within the limit stipulated by the National Fiscal Policy Policy | 4
1504 | This letter is from mForeign to SOC. mForeign does not object this proposal | 0
1504 | Continue 1504. mTransport and the State Railway of Thailand should carefully consider the project execution because the project involves a significant investment and is closely monitored by the public | 2 | 117

## r14
letter_id | item_description | issue_id | stakeholders_mentioned
1401 | mTransport requests the Cabinet to endorse an MOU to be signed by Thailand, China, and Lao PDR. The purpose of the MOU is to show the intention of connecting the Nong Khai to Vientiene via the high-speed train system. This MOU is a result of a Joint Meeting attended by the three countries in Beijing in 2019. | 4
1401a | This letter is from mForeign to mTransport. mTransport should revise the Thai document because its content does not match the English version | 4
1401a | Continue 1401a. This document is considered an international treaty and must be approved by the Cabinet. If mTransport believes that there is no significant impact to the economy or requiring an enactment of a new legislation, then the Parliament is not required to approve the document | 4

## r13
letter_id | item_description | issue_id | stakeholders_mentioned
1301 | mTransport proposes the Cabinet to issue a Royal Decree to survey areas for land expropriation along the Bangkok - Nakorn Ratchasima route. The proposal includes a tentative area of 957 land plots and 1130 buildings. | 4
1302 | This letter is from NESDC to SOC. The NESDC supports this proposal | 0
1302 | Continue 1302. The State Railway of Thailand should expropriate only the needed land area to minimize impact to the civilians and keep the project cost within the approved budget | 4 | 117
1302 | Continue 1302. The State Railway of Thailand should expedite the process so the project is on track for the commercial date of operation in 2024. | 1 | 117
1303 | This letter is from stateCouncil to SOC. The Cabinet has the authority to approve this proposal. | 4
1303 | Continue 1303. Once the Cabinet has approved this proposal, the State Railway of Thailand should review the attached 59 maps and submit the map along with the draft of the Royal Decree to the stateCouncil for further review | 4 | 117
1304 | This letter is from mAgriculture to SOC. mTransport should consider the impact to the drainage system from the construction | 2

## r12
letter_id | item_description | issue_id | stakeholders_mentioned
1201 | mTransport reports the HSRP progress to the Cabinet | 1
1202 | This letter is from NESDC to SOC. The State Railway of Thailand and mTransport should arrange the order of the construction work to promote domestic firms in partipating in the bidding process | 1 | 117
1202 | Continue 1202. Refering to the 3.5 km route (Klang Dong - Asoke), The State Railway of Thailand and the Department of Highway should draft MOU on Technical specifications, project framework, and expenditure plan according to rules and regulations | 4 | 117
1202 | Continue 1202. mTransport should have the Budget Bureau review the budget for the Klang Dong - Asoke route | 3
1203 | This letter is from the Budget Bureau to SOC. The State Railway of Thailand should execute the project in according with the rules and regulations | 4 | 117
1204 | This letter is from mFinance to SOC. The State Railway of Thailand should followed mFinance guideline on fund disimbursement in the electronic system | 4 | 117
1204 | Continue 1204. The construction of the 3.5 km (Klang Dong - Asoke route) might not achieve the economy of scale. The State Railway of Thailand should monitor the budget to avoid a cost overrun. | 2 | 117
1204 | Continue 1204. The State Railway of Thailand and the Department of Highway should specify the budget and the project timeline in their technical MOU | 1 | 117
1204 | Continue 1204. The State railway of Thailand and the Department of Highway should follow the relevant rules and regulations when entering the technical MOU | 4 | 117

## r11
letter_id | item_description | issue_id | stakeholders_mentioned
1101 | mTransport requests the Cabinet to endorse Contract 2.2 (Construction Supervision Consultant Services Agreement) worth 3.5 billion baht over 46 months | 4 | 117
1101a | This letter is from the Attorney General to mTransport. The letter is not available | 0
1102 | This letter is from NESDC to SOC. The State Railway of Thailand should modify the draft according to comments from the Attorney General before signing the contract | 4 | 117
1102 | Continue 1102. The State Railway of Thailand should consider an appropriate phasing of the civil work to support domestic contractors in entering the bid, promote transparency, and reduce the project cost | 1 | 117
1103 | This letter is from the stateCouncil to SOC. The contract will be signed between the State Railway of Thailand and both China Railway International and China Railway Design Corporation. This is in accordance with the Cooperation Framework. Since the contract specify that the enforcement is under Thai law, this contract is not an international treaty. The State Railway of Thailand should strictly follow the recommendations by the Attorney General | 4 | 117
1103 | Continue 1103. The Cabinet has the authority to approve this contract because the document is considered as part of the national policy agenda | 4
1103 | Continue 1103. The State Railway of Thailand should have a written endorsement from the NDRC that China Railway International and the China Railway Design Cooperation are the qualified counterparties for this contract | 4 | 117,207,216
1104 | This letter is from the Budget Bureau to SOC. The Budget Bureau supports this proposal. However, the State Railway of Thailand should strictly follow the relevant rules and regulations and follow the recommendations by the Attorney General before signing the contract | 4 | 117
1105 | This letter is from mForeign to SOC. This project is a significant investment and is a collaboration between the two countries. mTransport and the State Railway of Thailand should use utmore care when executing the project and adhere to all the rules and regulations | 4 | 117
1105 | Continue 1105. mTransport and the State Railway of Thailand should consider the following issues carefully: contract management, use of budget, safety standards, the feasibility of contract fulfillment, and contract clarity. This is to prevent any potential obstacle to execution the project and incuring negative impact to the bilateral relationship. Meanwhile, the State Railway of Thailand should protect the dignity and the credibility of Thailand when executing the project | 2 | 117
1105 | Continue 1105. This contract is not an international treaty because it is under the enforcement of Thai law | 4
1105 | Continue 1105. The contract involves a significant commitment from the national budget. Therefore, the contract should receive an approval from the Parliament | 3 | 130
1105 | Continue 1105. mTransport should publicize the HSRP because the public is highly interested in this project | 1
1106 | This letter is from mFinance to SOC. The State Railway of Thailand should modify the contract according to comments from the Attorney General before signing the contract | 4 | 117
1106 | Continue 1106. The civil work as described in Contract 2.1 will be separated into 4 phases. Therefore, the State Railway of Thailand should issue a Notice to Proceed to consultants as part of Contract 2.2 accordingly. This will keep the project cost within the approved budget | 1 | 117

## r10
letter_id | item_description | issue_id | stakeholders_mentioned
1001 | mTransport requests the Cabinet to endorse Contract 2.1 (Detailed Design Services Agreement). This contract is worth 1.7 billion baht with a duration of 10 months. The NDRC will select qualified Chinese contractors. The State Railway of Thailand will provide the necessary personal, equipment, and facilities to the contractor | 4 | 213,207,216
1001a | This letter is from the Attorney General to mTransport. The letter is not available | 0
1002 | This letter is from NESDC to SOC. The State Railway of Thailand should monitor the project within to be within 179 billion baht, which was the budget approved by the Cabinet | 3 | 117
1003 | This letter is from stateCouncil to SOC. Since the contract states the enforcement is under Thai law, this document is not an international treaty | 4
1003 | Continue 1003. mTransport should have a written endorsement from the NDRC that China Railway International and the China Railway Design Cooperation are the qualified counterparties for this contract | 4 | 213,207,216
1004 | This letter is from Budget Bureau to SOC. The State Railway of Thailand should strictly follow the relevant rules and regulations as well as consider what is best for the government and the public when executing this project | 4 | 117
1005 | This letter is from mForeign to SOC. Contract 2.1 is a procurement contract and is not considered an international treaty | 4
1005 | Continue 1005. The State Railway of Thailand should execute this project with utmost care and consider the bilateral relationship as well as protect the dignity and the credibility of Thailand | 1 | 117

## r09
letter_id | item_description | issue_id | stakeholders_mentioned
0901 | mTrasnport requests the Cabinet to approve the State Railway of Thailand to implement the HSRP (Bangkok - Nakorn Ratchasima Route) with a budget of 179 billion baht during the fiscal year 2017-2020. The proposal mentioned that NDRC would select qualified state-owned enterprises to enter the contract |  | 117,213
0901 | Continue 0901. Requests the Thai government to bear the full cost of the HSRP and to grant permission for the State Railway Enterprise to proceed with the loan process according to the State Railway Act | 3 | 117
0901 | Continue 0901. Requests the Parliament to approve the contracts required by the project | 4 | 130
0901a | This letter is from NESDC to mTransport. This project is considered as a strategic investment and is critical to Thailand becoming the regional logistic hub | 1
0901a | Continue 0901a. The HSRP is considered a national strategic investment. Although the project might not yield financial return, but the government should consider the economic return from the project | 3
0901a | Continue 0901a. The government should carefully conduct the cost-benefit analysis and make this information available to the public | 3
0901a | Continue 0901a. The procurement process should be under the Integrity Pact for transparency | 4
0901a | Continue 0901a. The government should instruct the Ministry of Transport to develop a comprehensive multimodal transportation plan. This plan should describes the development priorities, financial burden, and the Public-Private-Partnership guideline | 1
0901a | Continue 0901a. The government should reform the law to support domestic economic growth such as the city code and the use of land along the railway track | 4
0901a | Continue 0901a. The government should decrease its dependency on foreign expertise on high-speed rail technologies by training and educating domestic skill workers and establishing a research and development center | 2
0901a | Continue 0901a. The government should establish an agency independent from the State Railway of Thailand to execute the project | 1 | 117
0901a | Continue 0901a. The Cabinet should instruct mInterior to collaborate with the local governments to plan the development of the area surrounding the stations. Additionally, the city code should be revised to promote commercial land development | 1
0901a | Continue 0901a. mTransport should plan changes changes to the existing public transport system such that it will support the high-speed railway system. For example, by rerouting buses to the high-speed train stations | 1
0901b | This letter is from the Budget Bureau to mTransport. The letter is not available | 0
0902 | This letter is from stateCouncil to the SOC. This proposal is within the authority of the Cabinet to approve | 4
0902 | Continue 0902. The procurement process for the engineering design (civil works) is responsible by the State Railway of Thailand | 1 | 117
0902 | Continue 0902. Although mTransport has supplemented this proposal with comments from the NESDC, the correct process also requires that mTransport supplements this proposal with comments from the mFinance, Budget Bureau, and the State Enterprise Policy Committee before proposing to the Cabinet | 4
0902 | Continue 0902. Since the government must apportion a budget of 179 billion baht over four years, this project must receive an approval from the Parliament | 4 | 130
0902 | Continue 0902. If a contract to be signed as part of this project involves significant impact to the economy and is considered an international treaty, then that contract must also receive an approval from the Parliament according to Section 23 of the Constitution. | 4 | 130
0903 | This letter is from Budget Bureau to SOC. Since the NESDC has reviewed this project, the Budget Bureau supports this proposal. mTransport should strictly follow the recommendations by the NESDC | 0
0903 | Continue 0903. mFinance should consider domestic fundings options first | 3 | 117
0903 | Continue 0903. The State Railway of Thailand should proceed to register the loan as part of the Public Debt Management Plan FY2017 | 3
0903 | Continue 0903. mTransport should monitor the State Railway of Thailand that it follows the guidelines for compensation when conducting land expropriation | 4 | 117
0903 | Continue 0903. mTransport should monitor the State Railway of Thailand that it carefully conducts the cost appraisals according to the rules and regulations | 4 | 117
0903 | Continue 0903. The State Railway of Thailand shall negotiate with the bidders to secure the lowest cost for the construction contracts | 1 | 117
0903 | Continue 0903. The State Railway of Thailand should plan the project execution and project expenditure to manage the construction efficiently, and report the progress to mTransport every month | 1 | 117
0903 | Continue 0903. mTransport should communicate the benefits of the HSRP to the public | 1
0904 | This letter is from mForeign to mTransport. Since this project has a significant impact to the economy and the national budget, the mForeign does not object if mTransport decides to request an approval from the Parliament for any rising issues | 4 | 130
0904 | Continue 0904. mTransport’s plan to initiate the e-auction for the civil works is a process under domestic law and is not part of an international treaty | 4
0905 | This letter is from mFinance to SOC. This project involves a significant investment, but has a low financial return | 3
0905 | Continue 0905. Since some of the route segments are only 3.5 km or 11 km, potential bidders might not be interested in submitting tender for the construction works and could lead to a higher cost due to insufficient economy of scale | 1
0905 | Continue 0905. If the project commissions the engineering design of short route segment, then this could lead to a cost overrun. In this case, mTransport must request the Cabinet to approve the budget adjustment | 1
0906 | Continue 0905. Currently, mTransport does not have the engineering designs for all the routes and has not begin the land expropriation process. mTransport should be prepare these two steps in advance before beginning the construction. Otherwise, the project could encounter a cost overun or a delay | 2
0906 | Continue 0906. mTransport should consider planning for commercial land development along the route and plan to connect the high-speed railway network to the existing public transportation network | 1
0906 | Continue 0906. The State Railway of Thailand should have a concrete plan for the operation and management of the high-speed train system | 1 | 117
0906 | Continue 0906. mTransport should set-up an effective knowledge transfer program for operation and maintenance of the high-speed train system | 2
0906 | Continue 0906. mTransport and the State Railway of Thailand should promote the HSRP so there is demand from the public to use the high-speed train system and also demand from the private sector for commercial development along the route | 1 | 117
0906 | Continue 0906. Since the project will be funded by public debt, the State Railway of Thailand should include this project under the annual public debt management plan after the Cabinet has approved this proposal | 3 | 117

## r08
letter_id | item_description | issue_id | stakeholders_mentioned
0801 | mTransport requests the Cabinet to endorse an MOU between Thailand and China. This MOU explicitly mentions the construction of the Bangkok - Nakorn Ratchasima route is to begin by 2017. The document also states the Nakorn Ratchasima - Nong Khai route will begin shortly after Contract 2.1, 2.2, and 2.3 have been signed. | 4
0801a | This letter is from mForeign to mTransport. mForeign states that this MOU contain a clause that states both sides will begin constructing the Bangkok - Nong Khai route by early 2017 and that the Ratchasima - Nong Khai route will begin once all contracts required for the first route have been signed. However, this clause disagrees with the existing cooperation framework. Therefore, mTransport should consider whether this MOU changes what have already been agreed previously by Thailand and China. The MOU should clearly state which clauses from the cooperation framework that should still remain in effect and which clauses should be replaced by this MOU | 4
0801a | Continue 0801a. This MOU is an international treaty according to Article 23 of the Constitution and must receive an approval from the Cabinet. However, this document does not require an approval from the Parliament | 4
0802 | This letter is from NESDC to SOC. NESDC supports this proposal and recommends that mTransport expedite the HSRP so the project is completed within the timeline as discussed during the 16th Joint Meeting between Thailand and China | 1

## r07
letter_id | item_description | issue_id | stakeholders_mentioned
0701 | mTransport requests the Cabinet to endorse the revised Framework of Cooperation. This is a revision to the previously signed cooperation framework in 2015. The new version accommodates changes as a result of a meeting between the Prime Minister of Thailand and the Prime Minister of China in 2016. Specifically, the HSRP will focus on the BKK-Nakorn Ratchasima route as the initial stage, then proceed with the Nakorn Ratchasima - Nong Khai route. Additionally, Thailand will fund the HSRP by itself | 4 | 215,201
0701a | This letter is from mFinance to mTransport. mFinance has no objection to this proposal | 0
0701b | This letter is from mForeign to mTransport. The revised Cooperation Framework document is an international treaty according to Article 23 of the Constitution and must receive an approval from the Cabinet. However, the Parliament does not need to approve the document | 4
0702 | This letter is from mInterior to SOC. mInterior endorses the revised Cooperation Framework because it aligns with what was discussed during the bilateral meeting between the two Prime Ministers | 0
0703 | This letter is from mEnvironment to SOC. mEnvironment states that the HSRP must undergo the environmental impact assessment and the EIA report must be approved by the National Environment Committee | 2
0704 | This letter is from NESDC to SOC. The timeline for the first stage (Bangkok - Nakorn Ratchasima route) should take into account the time constraint required from the internal regulatory processes | 4
0704 | Continue from 0704. Future contracts under the HSRP should reserve the rights of Thailand to push forward its economic agenda such as developing talent in high-speed railway technology through training programs and establishing the high-speed train industry by setting up a manufacturing center in Thailand | 2
0705 | This letter is from the stateCouncil to SOC. stateConcil states that the revised cooperation framework is an international treaty according to Article 23 of the Constitution and must receive an approval from the Cabinet. However, the document does not require an approval from the Parliament | 4
0706 | This letter is from the Budget Bureau to SOC. The Budget Bureau states that if the loan terms from China Export and Import Bank is beneficial and not disadvantageous to Thailand, then the Cabinet should endorse the revised Cooperation Framework | 3 | 215
0707 | This letter is from mForeign to SOC. mForeign does not object the revised Cooperation Framework if the organizations involved could implement the agenda according to the governing rules and regulations | 4
0707 | Continue 0707. mForeigns opines the revised cooperation framework is an international treaty according to Article 23 of the Constitution and must receive an approval from the Cabinet. However, the document does not require an approval from the Parliament | 4

## r06
letter_id | item_description | issue_id | stakeholders_mentioned
0601 | mTransport reports the outcomes from the 6th-8th Joint Committee meeting to the Cabinet. The meeting summaries included issues such as CRC presenting the EPC for the civil works, CEXIM agreeing to submit details on the loan, technical traning program will be provided by Beijing Jiaotong University, the State Railway of Thailand working closely with consultants to conduct the environmental impact assessment | 1 | 204,215,201,117
0602 | This letter is from NESDC to SOC. mTransport should strictly adhere to the rules and regulations when executing the project | 4
0602 | Continue 0602. mTransport should thoroughly review the engineering design in terms of alignment with international standards and connecting to other mode of transportations planned in the Strategic Framework on Transport Infrastructure Development 2015-2022 | 1
0602 | Continue 0602. mTransport should coordinate with academic institutions in developing the technical training program | 2
0603 | This letter is from mForeign to SOC. mForeign does not object to the content of the meeting summary | 0
0604 | This letter is from mFinance to SOC. mFinance has no comments on this meeting summary | 0

## r05
letter_id | item_description | issue_id | stakeholders_mentioned
0501 | mTransport proposes the Cabinet to endorse the Framework of Cooperation. The document describes details on the planned railway routes, using EPC as the mode of cooperation, the delegation of tasks, the technology transfer program, and the loan from CEXIM. | 4 | 215201117
0501a | This letter is from mForeign to mTransport. mForeign comments that "Thailand", should precede "China" at every sentences in the document. | 4
0501a | Continue 0501a. The cooperation framework is classified as an international treaty and must receive an approval from the Cabinet. | 4
0502 | This letter is from mInterior to SOC. mInterior supports this proposal because the project should promote regional connectivity and strengthen the economic competitiveness | 0
0503 | This letter is from mForeign to SOC. mForeign states that the Framework of Cooperation describes commitments from Thailand such as setting-up a joint venture, funding the project, and conducting feasibility studies. Therefore, this is considered an international treaty and must be approved by the Cabinet according to Article 23 of the Constitution. However, this document does not require an approval from the Parliament | 4
0504 | This letter is from mFinance (the State Enterprise Policy Committee) to SOC. The Committee endorses the cooperation because the project should promote technology transfer to Thailand | 0
0504 | Continue 0504. mFinance should be involved with finding suitable sources of funding which must be done simultaneously with the cost-benefit assessment | 3
0504 | Continue 0504. The document should name Thai academic institutions and the private sector to participate in the project with the goal of supporting domestic R&D | 2
0504 | Continue 0504. mTransport should formulate a clear policy to promote research and development in high-speed railway technology | 2
0505 | This letter is from NESDC to SOC. The NESDC supports this proposal because the project aligns with the Strategic Framework for the Development of Transportation Infrastructure in Thailand 2015 - 2022 | 0
0506 | This letter is from stateCouncil to SOC. The document contains wording that imply legal obligation between both parties such as setting-up a special purpose vehicle, funding, and delegation of tasks. Therefore, this document is considered an international treaty according to the Article 23 of the Constitution | 4
0507 | This letter is from the Budget Bureau to the SOC. The Budget Bureau supports this proposal if the loan terms from the China Export and Import Bank is in the best interest of Thailand | 3 | 215
0508 | This letter is from the mEnvironment to the SOC. mEnvironment reports that they have evaluated two environmental assessment reports for the HSRP project in 2015. mEnvironment has notified the project owner [State Railway of Thailand] to submit additional supporting materials, but has yet to received any documents. If the current version of the HSRP project is different from the past HSRP, then the project owner should submit EIA reports promptly. | 2 | 117
0509 | This letter is from mFinance to SOC. mFinance recommends that the cost of taking out a loan from the China Export and Import Bank should not exceed the cost of taking out a loan from domestic or other sources | 3 | 215

## r04
letter_id | item_description | issue_id | stakeholders_mentioned
0401 | mTransport reports the outcome from the 5th Joint Committee Meeting to the Cabinet. The meeting summary mentions CRC presenting their engineering survey results, loan negogiation with CEXIM, China's willingness to support the State Railway of Thailand in setting up a testing center, etc. | 1 | 204,215,117
0402 | This letter is from mForeign to SOC. Since Thailand has signed an MOU with China on promoting agricultural products, this agricultural cooperation should also be driven along with the HSRP | 1
0402 | Continue 0402. Thailand should actively pursue its economic interests when negotiatiing funding, joint investment, and contracts | 1
0402 | Continue 0402. Since the HSRP has shown a significant progress, the government should also promote the development of other transportation modes as well (road, air, sea) | 1
0402 | Continue 0402. Thailand should push for its interests when drafting the framework of cooperation | 1
0402 | Continue 0402. The Framework of Cooperation should be signed after both sides are ready for the construction. mTransport should also propose the draft to the Cabinet for endorsement before signing | 1
0402 | Continue 0402. The meeting summary does not contain issues related to Article 23 of the Constitution (international treaty, binding agreement) | 4
0403 | This letter is from NESDC to SOC. mTransport should strictly follow to the relevant rules and regulations (with the goal of completing the project on time) | 4
0403 | Continue 0403. mTransport should minimize the project cost and the impact to residents by planing the HSRP to utilize the existing facilities | 2
0403 | Continue 0403. mTransport should develop the technical training program to include maintenance and electrical system | 2
0403 | Continue 0403. mTransport shoud promptly design an organizational structure to manage the railway system. The management structure might include moving foreward with creating the Department of Railways | 1

## r03
letter_id | item_description | issue_id | stakeholders_mentioned
0301 | mTransport reports the outcome from the 4th Joint Committee Meeting to the Cabinet. The meeting summary mentioned CRC will provide technical to Thai personnel, the negotiation with CEXIM to secure a loan, and the cooperation between CRC and the State Railway of Thailand in project planning | 1 | 204,215,117
0302 | This letter is from the NESDC to SOC. mTransport should strictly follow the rules and regulations when executing the project (with the goal of completing the project on time) | 4
0302 | Continue 0302. mTransport should promptly designate a department as the project owner so that the staffs from that department could undergo the necessary technical training | 2
0302 | Continue 0302. The cost of technical training should be evaluated as part of the cost-benefit analysis of the overall project | 3
0303 | This letter is from mForeign to SOC. mForeign is prepared to support with visa processing of foreign specialists | 1
0304 | This letter is from mFinance to SOC. mFinance supports the decision to create a joint venture to invest in the railway system and operation because this helps with risk management (by not having Thailand being the sole investor) | 3

## r02
letter_id | item_description | issue_id | stakeholders_mentioned
0201 | mTransport reports the progress of the HSRP to the Cabinet. The report includes outcomes from 1st-3rd Joint Committee meetings. Issues being mentioned: (1) CRC will construct the Bangkok - Kaeng Khoi route and Kaeng Khoi - MapTaPhut route (2) CREC will construct Kaeng Khoi - Nakorn Ratchasima route and Nakorn Ratchasima - Nong Khai route | 1 | 213,204,203,205,215,117
0201 | Continue 0201. mTransport also requested the Cabinet to endorse the request for support from other agencies and an MOU draft. | 1
0201 | Continue 0201. mTransport also requested the Cabinet to approve mFinance and Budget Bureau to support with the budget | 3
0201 | Continue 0201. mTransport also requested the Cabinet to endorse its request for support from other agencies | 1
0202 | This letter is from mInterior to SOC. mInterior reported that they have notified the provincial governors and local governments to support the project execution | 1
0203 | This letter is from mLabour to SOC. mLabour will provide support related to issuance of work permit to foreign specialists if the work permits would contribute to ecnonomic growth, labor market, and technological development | 4
0203 | Continue 0203. mLabour has the following recommendations: (1) The HSRP should focus on hiring Thai workers | 2
0203 | Continue 0203. (2) the HSRP should focus on technology transfer (3) creating skill transfer workshops to thai workers | 2
0203 | Continue 0203. mLabour has prepared and ensured that there are sufficient skilled workers for transport infrastructure development | 2
0204 | This letter is from stateCouncil to SOC. The proposed MOU is not considered an international treaty according to Article 23 of the Constitution because the document only details a broad cooperation framework | 4 | 213
0204 | Continue 0204. stateCouncil has no comment on the budget request if mFinance and the Budget Bureau have no objection to the budget proposal | 0
0204 | Continue 0204. The Cabinet has the authority to approve the relevant agencies to support mTransport in this project | 4
0205 | This letter is from NESDC to SOC. NESDC has a few comments (1) Clause 1 of the MOU draft states that Thailand will be responsible for land expropriation and environmental assessment, while China will be responsible for engineering design. The costs will be temporarily responsibled by each party. In this case, the Joint Committee must approve of these costs first | 3
0205 | Continue 0205. The MOU should explicitly state the project execution will strictly follow the domestic legislative framework. Also, the Cabinet should be involved with decisions on funding, sources of fund, and also approving the environmental impact assessment | 4
0205 | Continue 0205. The Budget Bureau should be involved with deciding the allocation of funds for this project | 1
0205 | Continue 0205. mTransport and the State Railway of Thailand should conduct a project feasibility study (on technical and economic aspects) and present the results to the Cabinet when requesting the Cabinet to approve the project later | 2 | 117
0205 | Continue 0205. The project steering committee should specify a mechanism to have domestic agencies work together in executing the project | 1
0205 | Continue 0205. mTransport should plan for the systematic management of all its railway routes and also plan to reform the organizational structure for railway management. These plans should be proposed to the Cabinet for endorsement | 2
0206 | This letter is from MDES (formerly Ministry of ICT) to SOC. Per mTransport's request for MDES to allocate a radio frequency channel for train operation, the allocation is the role and responsibility of the Office of The National Broadcasting and Telecommunications. | 1
0207 | This letter is from mInnovation to SOC. Domestic firms have the capability to do all the civil works. Domestic firms only lacked the capability to complete 100% of the track work. Therefore, the project should open up for domestic firms to participate | 1
0207 | Continue 0207. If the HSRP is developing a new railway system; then the civil works, track works, signaling system, and carriage design should be considered in simultaneously | 1
0207 | Continue 0207. The feasibility study should be conducted by an independent organization to avoid any conflict of interest | 2
0207 | Continue 0207. The environmental impact assessment should follow the domestic legal requirements | 4
0207 | Continue 0207. Land expropriation should follow the domestic legal requirements | 4
0207 | Continue 0207. The system work should use domestic parts and hire local engineers | 2
0207 | Continue 0207. Domestic firms should be responsible for the train operation. Train maintenance could be a joint venture between domestic and Chinese firms | 1
0207 | Continue 0207. The loan terms should be comparable or better than JICA's | 3
0207 | Continue 0207. The MOU should include concrete details on the technology transfer process | 2
0207 | Continue 0207. The issue proposal should include GISDA (an agency under mInnovation) to support with geographic information system tasks | 1
0207 | Continue 0207. The project should hire local talents to work on engineering design, construction, operation and maintenance | 2
0207 | Continue 0207. The Thailand Institute of Scientific and Technological Research (under mInnovation) can provide testing and certification of critical components such as sleeper, track, and fastener | 1
0208 | This letter is from the mDefence to SOC. The letter is not available | 0
0209 | This letter is from mForeign to SOC. The letter is not available | 0

## r01
letter_id | item_description | issue_id | stakeholders_mentioned
0101 | mTransport requests the Cabinet to endorse the MOU on development railway infrastructure as part of the National Strategic Framework on Transport Infrastructure Development 2015-2022 | 4 | 213
0102 | This letter is from Attorney General to SOC. The Attorney General has no further comment on the MOU | 0
0103 | This letter is from the Budget Bureau to SOC. The HSRP is a significant investment. Therefore, mTransport should ensure that the project complies with the existing rules and regulations (does not specify in which aspects) | 4
0104 | This letter is from mForeign to SOC. The proposed MOU is considered an international treaty. mForeign does not object if mTransport will submit the MOU document to the Parliament for endorsement | 4 | 130
0105 | This letter is from NESDC to SOC. Since the HSRP is a collaboration between both countries, the project will strengthen the bilateral relationship | 0
0105 | Continue 0105. The project should support the national development and promote the connection between Thailand and its neighboring countries in ASEAN as well as the Southern part of China | 2
0105 | Continue 0105. mTransport should review and ensure the National Railway Development Plan aligns with the railway development direction of the neighboring countries | 2
0105 | Continue 0105. mTransport should compare the cost-benefit of railway systems of different speeds | 3
0105 | Continue 0105. mTransport consider the most beneficial form of cooperation, especially considering the rights to land development along the railway routes | 1
0105 | Continue 0105. mTransport should ensure an effective technology transfer program | 2
0105 | Continue 0105. mTransport should reserve the right of the Thai government to decide the type of investment for procuring carriages and who to operate and maintain the system according to the Thai rules and regulations | 4
0106 | Continue 0105. This letter is from the stateCouncil to SOC. Although the MOU draft is an international treaty, the document only states a broad cooperation framework. Therefore, the document does not require an endorsement from the Parliament according to Article 23 of the Constitution | 4